## Assessment Guidelines
Source: ISO/IEC 15504-2 | Source: Varkoi, T., Self-Assessment Deployment Package

## Analysis
Software Engineering — Lifecycle Profiles for Very Small Entities (VSEs) — Part 5-1: Management and Engineering Guide - Basic VSE Profile
Project Management
PM.1 | Project Planning | #REF!
PM.2 | Project plan execution
PM.3 | Project assessment and control
PM.4 | Project closure
Software Implementation
SI.1 | Software Implementation Initiation
SI.2 | Software Requirement Analysis
SI.3 | Software Architectural and Detailed Design
SI.4 | Software Construction
SI.5 | Software Integration and Tests
SI.6 | Product Delivery

## Proj Planning
The Project Planning activity documents the planning details needed to manage the project.
Goals: PM.O1, PM.O5, PM.O6, PM.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | PM.1.1 Review the Statement of Work | Statement of Work
2 | PM.1.2 Define with the Customer the Delivery Instructions of each one of the deliverables specified in the Statement of Work. | Delivery Instructions
3 | PM.1.3 Identify the specific tasks to be performed in order to produce the deliverables and their software components identified in the Statement of Work. | Tasks
4 | PM.1.4 Establish the Estimated Duration to perform each task. | Tasks
5 | PM.1.5 Identify and document the resources: human, material, equipment and tools, including the required training of the Work Team to perform the project. Include in the schedule the dates when resources and training will be needed. | Resources
6 | PM.1.6 Establish the Composition of Work Team assigning roles and responsibilities according to the Resources. | Composition of Work Team
7 | PM.1.7 Assign estimated start and completion dates to each one of the tasks in order to create the Schedule of the Project Tasks taking into account the assigned resources, sequence and dependency of the tasks. | Schedule of the Project Tasks
8 | PM.1.8 Calculate and document the project Estimated Effort and Cost. | Estimated Effort and Cost
9 | PM.1.9 Identify and document the risks which may affect the project. | Identification of Project Risks
10 | PM.1.10 Document the Version Control Strategy in the Project Plan. | Version Control Strategy
11 | PM.1.11 Generate the Project Plan or update it. Furthermore, the Project Plan can be updated due to the Change Request made by the Customer or arising from the project. | Project Plan
12 | PM.1.12 Include product description, scope, objectives and deliverables in the Project | Project Plan
Overall assessment result:

## Proj Plan Exe
The Project Plan Execution activity implements the documented plan on the project
Goals: PM.O2, PM.O3, PM.O4, PM.O5, PM.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | PM.2.1 Review the Project Plan and record actual data in Progress Status Record. | Progress Status Record
2 | PM.2.2 Analyze and evaluate the Change Request for cost, schedule and technical impact, and include the accepted changes in the Project Plan. | Change Request[evaluated] Project Plan[changed]
3 | PM.2.3 Conduct revision meetings with the Work Team, review risk status, record agreements and track them to closure. | Meeting Record [updated]
5 | PM.2.4 Conduct revision meetings with the Customer, record agreements and track them to closure. | Meeting Record [updated] Change Request[accepted]
6 | PM.2.5 Perform backup according to the Version Control Strategy. | Project Repository Backup
7 | PM.2.6 Perform Project Repository recovery using the Project Repository Backup, if necessary. | Project Repository [recovered]
Overall assessment result:

## Proj Assessment & Control
The Project Assessment and Control activity monitors and evaluates the performance of the plan against documented commitments
Goals: PM.O2
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | PM.3.1 Evaluate project progress with respect to the Project Plan comparing: - actual tasks against planned tasks - actual results against established project objectives - actual resource allocation against planned resources - actual cost against budget estimates - actual time against planned schedule - actual risk against previously identified | Progress Status Record [evaluated]
2 | PM.3.2 Establish actions to correct deviations or problems and identified risks concerning the accomplishment of the plan, as needed, document them in Correction Register and track them to closure. | Correction Register
3 | PM.3.3 Identify changes to requirements and/or Project Plan to address major deviations, potential risks or problems concerning the accomplishment of the plan, document them in Change Request and track them to closure. | Change Request[initiated]
Overall assessment result:

## Proj Closure
The Project Closure activity provides the project’s documentation and products in accordance with contract requirements
Goals: PM.O2
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | PM.4.1. Formalize the completion of the project according to the Delivery Instructions established in the Project Plan, providing acceptance support and getting the Acceptance Record signed. | Acceptance Record Software Configuration [accepted]
2 | PM.4.2 Update Project Repository. | Project Repository [updated]
Overall assessment result:

## Soft Impl Initiation
The Software Implementation Initiation activity ensures that the Project Plan established in Project Planning activity is committed to by the Work Team.
Goals: SI.O1
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | SI.1.1 Revision of the current Project Plan with the Work Team members in order to achieve a common understanding and get their engagement with the project. | Project Plan[reviewed]
2 | SI.1.2 Set or update the implementation environment.
Overall assessment result:

## Soft Requir Analysis
The Project Assessment and Control activity monitors and evaluates the performance of the plan against documented commitments
Goals: SI.O2, SI.O6, SI.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | SI.2.1 Assign tasks to the Work Team members in accordance with their role, based on the current Project Plan.
2 | SI.2.2 Document or update the Requirements Specification. Identify and consult information sources (customer, users, previous systems, documents, etc.) in order to get new requirements. Analyze the identified requirements to determinate the scope and feasibility. Generate or update the Requirements Specification. | Requirements Specification
3 | SI.2.3 Verification of the Requirements Specification. Verify the correctness and testability of the Requirements Specification and its consistency with the Product Description. Additionally, review that requirements are complete, unambiguous and not contradictory. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. | Verification Results Requirements Specification [verified] Change Request [initiated]
4 | SI.2.4 Validation of the Requirements Specification Validate that Requirements Specification satisfies needs and agreed upon expectations, including the user interface usability. The results found are documented in a Validation Results and corrections are made until the document is approved by CUS. | Validation Results Requirements Specification [validated]
5 | SI.2.5 Document the preliminary version of the Software User Documentation or update the present manual. (optional) | Software User Documentation [preliminary]
6 | SI.2.6 Verification of the Software User Documentation Verify consistency of the Software User Documentation with the Requirement Specification. .The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. (optional) | Verification Results Software User Documentation [preliminary, verified] Change Request [initiated]
7 | SI.2.7 Incorporate the Requirements Specification, and *Software User Documentation to the Software Configuration in the baseline. *(optional) | Specification [validated, baselined], *Software User Documentation[preliminary, verified, baselined]
Overall assessment result:

## Soft Arch & Detail Design
The Software Architectural and Detailed Design activity transforms the software requirements to the system software architecture and software detailed design.
Goals: SI.O3, SI.O6, SI.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | SI.3.1 Assign tasks to the Work Team members related to their role according to the current Project Plan.
2 | SI.3.2 Understand Requirements Specifications.
3 | SI.3.3 Document or update the Software Design: Analyze the Requirements Specification to generate the architectural design, its arrangement in subsystems and software components defining the internal and external interfaces. Describe in detail, the appearance and the behavior of the interface, based on the Requirements Specification in a way that resources for its implementation can be foreseen. Provide the detail of software components and their interfaces to allow the construction in an evident way. Generate or update the Traceability Record. | Software Design Traceability Record
4 | SI.3.4 Verification of the Software Design Verify correctness of Software Design documentation, its feasibility and consistency with their Requirement Specification. Verify that the Traceability Record contains the adequate relationships between requirements and the Software Design elements. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. | Verification Results Software Design[verified] Traceability Record[verified] Change Request [initiated].
5 | SI.3.5 Establish or update Test Cases and Test Procedures for integration testing based on Requirements Specification and Software Design. Customer provides testing data, if needed | Test Cases and Test Procedures
6 | SI.3.6 Verification of the Test Cases and Test Procedures. Verify consistency among Requirements Specification, Software Design and Test Cases and Test Procedures. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. | Verification Results Test Cases and Test Procedures[verified]
7 | SI.3.7 Update the Traceability Record incorporating the Test Cases and Test Procedures. | Traceability Record [updated]
8 | SI.3.8 Incorporate the Software Design, Test Cases, Test Procedures and Traceability Record to the Software Configuration as part of the baseline. | Software Configuration Software Design[verified, baselined] Test Cases and Test Procedures[verified] Traceability Record[verified, baselined]
Overall assessment result:

## Soft Construction
The Software Construction activity develops the software code and data from the Software Design.
Goals: SI.O4, SI.O6, SI.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | SI.4.1 Assign tasks to the Work Team members related to their role, according to the current Project Plan.
2 | SI.4.2 Understand Software Design.
3 | SI.4.3 Construct or update Software Components based on the detailed part of the Software Design and define or update unit test cases. | Software Components
4 | SI.4.4 Apply unit test cases to verify that functions work accordingly to the detailed part of the Software Design. | Software Components[unit tested]
5 | SI.4.5 Correct the defects found until successful unit test (reaching exit criteria) is achieved. | Software Components[corrected]
6 | SI.4.6 Update the Traceability Record incorporating Software Components constructed or modified. | Traceability Record[updated]
7 | SI.4.7 Incorporate Software Components and Traceability Record to the Software Configuration as part of the baseline. | Software Configuration Software Components[corrected, baselined] Traceability Record[updated baselined]
Overall assessment result:

## Soft Integration & Tests
The Software Integration and Test activity ensures that the integrated software components satisfy the software requirements.
Goals: SI.O5, SI.O6, SI.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | SI.5.1 Assign tasks to the work team members related to their role, according to the current Project Plan.
2 | SI.5.2 Understand Test Cases and Test Procedures. Set or update the testing environment.
3 | SI.5.3 Integrates the Software using Software Components and defines or updates Test Cases and Test Procedures for integration. | Software Test Cases and Test Procedures
4 | SI.5.4 Perform tests using Test Cases and Test Procedures for integration and document results in Test Report. | Software [tested] Test Report
5 | SI.5.5 Correct the defects found until successful test (reaching exit criteria) is achieved. | Software [corrected] Test Report [defects eliminated]
6 | SI.5.6 Updates the Traceability Record if appropriate. | Traceability Record[updated]
7 | SI.5.7 Document the Product Operation Guide or update the current guide, if appropriate. | Product Operation Guide
8 | SI.5.8 Verification of the Product Operation Guide , if appropriate (see SI.5.7) Verify consistency of the Product Operation Guide with the Software. The results found are documented in a Verification Results and corrections are made until the document is approved by PR. | Verification Results Product Operation Guide[verified
9 | SI.5.9 Document the Software User Documentation or update the current one, if appropriate. | Software User Documentation
10 | SI.5.10 Verification of the Software User Documentation, if appropriate (see SI.5.9) Verify consistency of the Software User Documentation with the Software. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. | Verification Results Software User Documentation[verified]
11 | SI.5.11 Incorporate the Software, Traceability Record, Test Report, Product Operation Guide and Software User Documentation to the Software Configuration as part of the baseline. | Software Configuration Software[tested, baselined] Traceability Record[updated, baselined] Test Report [baselined] Product Operation Guide [verified, baselined] Software User Documentation [verified, baselined]
Overall assessment result:

## Product Delivery
The Product Delivery activity provides the integrated software product to the Customer.
Goals: SI.O6, SI.O7
Tasks |  |  | Assessment
Number | Description | Evidence (e.g. outputs) | Not Achieved (N) | Partially Achieved (P) | Largely achieved (L) | Fully achieved (F) | Notes
1 | SI.6.1 Assign tasks to the work team members related to their role, according to the current Project Plan.
2 | SI.6.2 Understand Software Configuration.
3 | SI.6.3 Document the Maintenance Documentation or update the current one. | Maintenance Documentation
4 | SI.6.4 Verification of the Maintenance Documentation. Verify consistency of Maintenance Documentation with Software Configuration. The results found are documented in a Verification Results and corrections are made until the document is approved by DES. | Verification Results Maintenance Documentation [verified]
5 | SI.6.5 Incorporate the Maintenance Documentation as baseline for the Software Configuration. | Software Configuration Maintenance Documentation[verified, baselined]
6 | SI.6.6 Perform delivery according to Delivery Instructions. | Software Configuration [delivered]
Overall assessment result: